## GanttChart
Gantt Chart |  |  |  |  | 68
YEAR 1
[42] | [5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
WBS | Tasks | Start | End | Duration (Qtrs) |  | Oct-Dec 2009 |  |  |  |  | Jan-Mar 2010 |  |  |  |  | Apr-June 2010 |  |  |  |  | July-Sept 2010 |  |  |  |  | Oct-Dec 2010 |  |  |  |  | Jan-Mar 2011 |  |  |  |  | Apr-June 2011 |  |  |  |  | July-Sept 2011 |  |  |  |  | Oct-Dec 2011 |  |  |  |  | Jan-Mar 2012 |  |  |  |  | Apr-June 2012 |  |  |  |  | July-Sept 2012 | Oct-Dec 2012
YEAR 1 | 1ST QUARTER - January 1, 2010 to March 31, 2010
1.1 | Organization X to gauge interest about program participaton | 2010-01-01 | 2010-01-31
1.2 | Interested parties to notify organization X of their interest | 2010-01-01 | 2010-01-31
1.3 | Staff conducts literature search on engaging fathers | 2010-01-01 | 2010-03-31
1.4 | Staff conducts literature search on assessment tools to engage fathers | 2010-01-01 | 2010-03-31
1.5 | Fatherhood Engagement experts are identified | 2010-01-01 | 2010-01-15
1.6 | Organizations and County partipants are finalized | 2010-02-01 | 2010-02-28
1.6.1 | - Counties asked to identify effective strategies for engaging fathers | 2010-02-01 | 2010-02-28
1.7 | Convene 1st Engaging and Working with Fathers Meeting | 2010-03-04 | 2010-03-04
2 | 2ND QUARTER - April 1, 2010 to June 30, 2010
2.1 | Father Engagement Committee assesses utility of assessment tools | 2010-04-01 | 2010-06-30
2.2 | Father Engagement Committee drafts/edits assessment tools | 2010-04-01 | 2010-05-31
2.3 | Engaging and Working with Fathers Webinar | 2010-06-24 | 2010-06-24
2.3.1 | - Progress report update | 2010-06-24 | 2010-06-24
3 | 3RD QUARTER - July 1, 2010 to September 30, 2010
3.1 | Father Engagement Committee finalizes assessment tool | 2010-07-06 | 2010-07-06
3.2 | Convene Engaging and Working with Fathers webinar | 2010-08-25 | 2010-08-25
3.3 | Data Collection and Analysis - Organizational Assessment Tool | 2010-09-24 | 2010-09-30
4 | 4TH QUARTER - October 1, 2010 to December 31, 2010
4.1 | Data Collection and Analysis - Organizational Assessment Tool | 2010-10-01 | 2010-10-19
4.2 | Convene 2nd Engaging and Working with Fathers Meeting | 2010-10-19 | 2010-10-19
Engaging and Working Effectively with Fathers in the Child Welfare System
WBS | Tasks | Start | End | Duration (Qtrs) |  | Oct-Dec 2009 |  |  |  |  | Jan-Mar 2010 |  |  |  |  | Apr-June 2010 |  |  |  |  | July-Sept 2010 |  |  |  |  | Oct-Dec 2010 |  |  |  |  | Jan-Mar 2011 |  |  |  |  | Apr-June 2011 |  |  |  |  | July-Sept 2011 |  |  |  |  | Oct-Dec 2011 |  |  |  |  | Jan-Mar 2012 |  |  |  |  | Apr-June 2012 |  |  |  |  | Jul-Sept 2012 | Oct-Dec 2012
YEAR 2
YEAR 2 | 1ST QUARTER - January 1, 2011 to March 31, 2011
1.1 | 1st round father engagement strategies have been identified | 2010-10-01 | 2011-06-30
1.2 | 1st round father engagement strategies have been implemented | 2010-10-01 | 2012-06-30
1.3 | Conference call/webinar | 2011-03-15 | 2011-03-15
2 | 2ND QUARTER - April 1, 2011 to June 30, 2011
2.1 | Evaluate 1st round father engagement strategies | 2011-02-01 | 2012-06-30
2.2 | 2nd round of father engagement strategies have been identified | 2010-05-01 | 2012-06-30
2.3 | 2nd round of father engagement strategies have been implemented | 2011-05-01 | 2012-06-30
2.4 | Evaluate 2nd round father engagement strategies | 2010-05-01 | 2012-06-30
2.5 | Convening: Assessing round 1 and round 2 engagement strategies | 2011-06-15 | 2011-06-15
3 | 3RD QUARTER - July 1, 2011 to September 30, 2011
3.1 | Conduct up to five training sessions to support father engagement strategies | 2010-10-01 | 2012-12-30
3.2 | Conference call/webinar | 2011-08-15 | 2011-08-15
4 | 4TH QUARTER - October 1, 2011 to December 31, 2011
4.1 | Convening: Planning for year 3 | 2011-12-01 | 2011-12-01
YEAR 3
YEAR 3 | 1ST QUARTER - January 1, 2012 to March 31, 2012
1.1 | Analyze results of statewide pilot (round 1 and 2) | 2012-01-01 | 2012-06-30
1.2 | Convene Engaging and Working with Fathers phone meeting/webinar | 2012-03-01 | 2012-03-30
2 | 2ND QUARTER - April 1, 2012 to June 30, 2012
2.1 | Finalize statewide report | 2012-04-01 | 2012-09-30
2.2 | Draft policy paper | 2012-04-01 | 2012-09-30
2.3 | Convene Engaging and Working with Fathers in-person Meeting | 2012-06-01 | 2012-06-30
WBS | Tasks | Start | End | Duration (Qtrs) |  | Oct-Dec 2009 |  |  |  |  | Jan-Mar 2010 |  |  |  |  | Apr-June 2010 |  |  |  |  | July-Sept 2010 |  |  |  |  | Oct-Dec 2010 |  |  |  |  | Jan-Mar 2011 |  |  |  |  | Apr-June 2011 |  |  |  |  | July-Sept 2011 |  |  |  |  | Oct-Dec 2011 |  |  |  |  | Jan-Mar 2012 |  |  |  |  | Apr-June 2012 |  |  |  |  | Jul-Sept 2012 | Oct-Dec 2012
3 | 3RD QUARTER - July 1, 2012 to September 30, 2012
3.1 | Finalize policy paper | 2012-07-01 | 2012-12-30
3.2 | Disseminate findings from statewide implementation and policy paper | 2012-08-01 | 2012-12-30
3.3 | Integrate findings and revise curricula for: | 2012-08-01 | 2012-12-30
3.3.1 | - Line staff | 2012-08-01 | 2012-12-30
3.3.2 | - Supervisors | 2012-08-01 | 2012-12-30
3.3.3 | - IVE students | 2012-08-01 | 2012-12-30
4 | 4TH QUARTER - October 1, 2012 to December 31, 2012
4.1 | Disseminate findings and policy paper con't. | 2012-10-01 | 2012-12-30
4.2 | Convene Engaging and Working with Fathers in-person Meeting | 2012-10-01 | 2012-10-30
Note on A7: Work Breakdown Structure Enter the Task# and Subtask# 2 2.1 2.2 etc.
Note on F7: End Date The ending date is calculated by adding the Duration (calendar days) to the Start date minus 1 day, because the task duration is from the beginning of the Start day to the end of the End day.
Note on E7: Start Date Enter the starting date for this task. To associate the start date with the end of another task, enter a formula in the start date that refers to the end date of that task.
Note on D14: Administrator: Several experts to be identified by CDSS
Note on D17: Administrator: 1.6.1 - 1.6.3
Note on A34: Work Breakdown Structure Enter the Task# and Subtask# 2 2.1 2.2 etc.
Note on E34: Start Date Enter the starting date for this task. To associate the start date with the end of another task, enter a formula in the start date that refers to the end date of that task.
Note on F34: End Date The ending date is calculated by adding the Duration (calendar days) to the Start date minus 1 day, because the task duration is from the beginning of the Start day to the end of the End day.
Note on A62: Work Breakdown Structure Enter the Task# and Subtask# 2 2.1 2.2 etc.
Note on E62: Start Date Enter the starting date for this task. To associate the start date with the end of another task, enter a formula in the start date that refers to the end date of that task.
Note on F62: End Date The ending date is calculated by adding the Duration (calendar days) to the Start date minus 1 day, because the task duration is from the beginning of the Start day to the end of the End day.
Sample Note
Sample Note
Sample Note
Engaging and Working Effectively with Fathers in the Child Welfare System
Engaging and Working Effectively with Fathers in the Child Welfare System