RFA/CCR Implementation Guide for Counties

Suggested Committees/workgroups:

- Steering Committee – Provides leadership, planning, program oversight and decision making

- Data Committee – Identify, track, and monitor data related to RFA

- Training Committee – Engagement of Stakeholder, training plans

- Implementation & Policy Team – internal implementation group to develop policy and procedures

- Placement Workgroup – Identify changes to existing placement resources, engage stakeholders, etc.

| January Milestone: Commence Steering Committee | Completed |
| --- | --- |
| Week 1 1/25/16 | Task: Identify and invite members to the Steering Committee Task: Set up bi-weekly meeting schedule |  |
| February Milestone #1: Complete Workload Data Analysis Milestone #2: Conduct Readiness Assessment Milestone #3: Convene Training Committee Milestone #4: Develop staffing plan | Completed |
| Week 2 2/1/16 | Steering Committee | Task: Review Assembly Bill (AB) 403 in order to develop understanding of CCR framework and new requirements. http://www.leginfo.ca.gov/pub/11-12/bill/sen/sb_1001-1050/sb_1013_bill_20120627_chaptered.pdf Task: Conduct Readiness Assessment http://www.cdsscounties.ca.gov/rfa/res/pdf/ReadinessCountyAssessment.pdf Complete sections 1, 2, 3, 6, 7 |  |
|  | Data Unit | Task: Begin Workload Data Analysis, completing Section III Planning Tools of RFA Implementation Guide (Appendix A of Readiness Assessment) (See Riverside County example) |  |
| Week 3 2/8/16 | Data Unit | Task: Complete and disseminate Workload Data Analysis to all workgroups |  |
| Week 4 2/15/16 | Steering Committee | Task: Review and discuss Workload Data Analysis Task: Complete Section IV Leadership (RFA Implementation Guide); identifying the organizational structure the county will use to manage RFA |  |
|  | Training Committee | Task: Develop Engagement and Training plan for internal and external staff, completing Section VI Training Tools of RFA Implementation Guide |  |
| Week 5 2/22/16 |  |  |  |
| Week 6 2/29/16 | Steering Committee | Task: Develop Staffing Plan – identify staffing resources and how RFA/CCR will be managed from line level through management level. Task: Disseminate Staffing Plan to Implementation & Policy team. |  |
|  | Training Committee | Task: Continue to develop engagement and training plan. |  |
| March Milestone #1: Convene Implementation and Policy Team Milestone #2: Plan staff training and Stakeholder meetings |
| Week 7 3/7/16 | Implementation & Policy Team | Task: Commence Implementation & Policy Team; meet bi-weekly Task: Orient team to AB403; Disseminate and review Workload Data Analysis, and Staffing Plan Task: Review Section V Policy and Procedures Tools of RFA Implementation Plan |  |
| Week 8 3/14/16 | Steering Committee | Task: Continue to monitor RFA implementation and make required policy decisions. Disseminate decisions to workgroups as needed. |  |
|  | Training Committee | Task: Continue to develop engagement and training plan. Task: Plan for RFA/CCR 101 training for staff. |  |
| Week 9 3/21/16 | Implementation & Policy Team | Task: Review current policies and procedures related to current licensing, relative approval and adoption programs. Identify areas that need focus for new program (i.e. permanency assessments, home assessments, written assessments, etc.) |  |
| Week 10 3/28/16 | Steering Committee | Task: Continue to monitor RFA implementation and make required policy decisions. Disseminate decisions to workgroups as needed. |  |
|  | Training Committee | Task: Plan for Stakeholder meetings or orientation to RFA |  |
| April Milestone #1: Train all staff to RFA/CCR 101 (Overview) Milestone #2: Complete Policy Plan Milestone #3: Convene Placement Workgroup |
| Week 11 4/4/16 | Implementation & Policy Team | Task: Identify all policies that need update or need to be written. |  |
| Week 12 4/11/16 | Steering Committee | Task: Continue to monitor RFA implementation and make required policy decisions. Disseminate decisions to workgroups as needed. |  |
|  | Training Committee | Train Staff to RFA/CCR 101 |  |
| Week 13 4/18/16 | Implementation & Policy Team | Task: Submit Policy plan to Steering committee. Task: Assess existing child and family teaming practices/protocols to build on (Wraparound, Team Decision-making Meetings, Katie A Core Practice Model, etc.). |  |
|  | Steering Committee | Task: Review Policy Plan and make required decisions. |  |
| Week 14 4/25/16 | Placement Workgroup | Task: Determine anticipated placement needs related to RFA, FFAs, and STRTCs. Collaborate with local providers to identify placement resources and any gaps. Identify FFA’s that are accredited. Revise any contracts as necessary. |  |
| May Milestone #2: Hold external stakeholder meetings to introduce RFA/CCR |
| Week 15 5/2/16 | Implementation & Policy Team | Task: Continue to address policies and procedures, beginning to develop RFA policy and procedures. Reference Written Directives and CDSS RFA website. |  |
|  | Training Committee | Hold Stakeholder Orientation Meetings |  |
| Week 16 5/9/16 | Steering Committee |  |  |
| Week 17 5/16/16 |  |  |  |
| Week 18 5/23/16 | Placement Workgroup | Task: Identify new foster parent retention, recruitment and support activities. Task: Determine RFA family training requirements including preapproval and annual training needs. |  |
|  | Steering Committee |  |  |
| Week 19 5/30/16 | Training Committee | Task: Debrief RFA/CCR 101 training and Stakeholder Orientation meetings. |  |
| June Milestone #1: Finalize RFA/CCR model Milestone #2: Complete Placement Resources Action Plan |
| Week 20 6/6/16 | Steering Committee |  |  |
| Week 21 6/13/16 | Implementation & Policy Team | Task: Finalize RFA/CCR model and submit to Steering Committee for review. |  |
| Week 22 6/20/16 | Steering Committee | Task: Review RFA/CCR model; approve or make adjustments as needed |  |
| Week 23 6/27/16 | Placement Workgroup | Task: Complete Placement Resources Action Plan which identifies the counties needs and plan of action. Submit to the Steering Committee. |  |
| July Milestone #1: Identify all resources (staff, space, technology, etc.) need to implement RFA/CCR model |
| Week 24 7/4/16 | Steering Committee | Task: Identify resources needed to implement the model and develop plan of action Task: Review Placement Resources Action Plan; Make decisions as needed. |  |
| Week 25 7/11/16 | Placement Workgroup | Task: Work on Action Plan |  |
| Week 26 7/18/16 | Steering Committee | Task: Identify resources needed to implement the model and develop plan of action |  |
| Week 27 7/25/16 |  |  |  |
| August Milestone #1: Finalize RFA Model Milestone #2: Select RFA staff, as needed Milestone #3: Develop method for monitoring Implementation (data tracking, evaluation, etc.) |
| Week 28 8/1/16 | Steering Committee | Task: Finalize RFA Model |  |
| Week 29 8/8/16 |  | Implement staff selection plan |  |
| Week 30 8/15/16 | Steering Committee |  |  |
| Week 31 8/22/16 |  |  |  |
| Week 32 8/29/16 | Steering Committee |  |  |
| September Milestone #1: Train all staff to RFA Milestone #2: Select Child and Family Team model & develop protocols |
| Week 33 9/5/16 |  | Train staff to RFA Model |  |
| Week 34 9/12/16 | Steering Committee |  |  |
| Week 35 9/19/16 |  |  |  |
| Week 36 9/26/16 | Steering Committee |  |  |
| October Major Milestone: Train RFA Staff |
| Week 37 10/3/16 |  |  |  |
| Week 38 10/10/16 | Steering Committee |  |  |
| Week 39 10/17/16 |  |  |  |
| Week 40 10/24/16 | Steering Committee |  |  |
| Week 41 10/31/16 |  |  |  |
| November Milestone #1: Train staff to Child and Family Team Meetings model |
| Week 42 11/7/16 | Steering Committee |  |  |
| Week 43 11/14/16 |  |  |  |
| Week 44 11/21/16 | Steering Committee |  |  |
| Week 45 11/28/16 |  |  |  |
| December |
| Week 46 12/5/16 | Steering Committee |  |  |
| Week 47 12/12/16 |  |  |  |
| Week 48 12/19/16 | Steering Committee |  |  |
| Week 49 12/26/16 |  |  |  |
| January 2017 Milestone #1: Implement RFA/CCR Model Milestone #2: Monitor Implementation |
| Week 50 1/2/17 | Steering Committee | GO LIVE |  |