\*Updated 10.14.13

**Pathways to Well Being Overview Training –** 3 hr module

* Includes: Class/Subclass identification; Terms to know; Purpose/use of screening tool; Next steps after screening; Engagement strategies
* Audience: CWS Staff, BHS staff and providers
* eLearnings are pre-requisites for trainers & trainees
* Class to be co-trained by BHS and CWS SME’s
* Design completion: Jan; Roll out: Feb – Mar. 14

*Curriculum Lead: PCWTA; Contract: PCWTA*

**Katie A. Overview -** 1 hr

* eLearning for CWS and CYF BHS staff and providers
* Completed: Aug. 1
* Audience: CWS staff, BHS staff, BHS providers

*Curriculum Lead: PCWTA; Contract: PCWTA*

**CWS Overview for BHS Staff/Providers-** 1 hr

* eLearning
* To include: SOP terms, SDM overview, CWS screening tool, court timelines and what reports to ask for
* Target completion: Nov-2013
* Audience: BHS Staff and Providers

*Curriculum Lead: PCWTA; Contract: PCWTA*

**CYF BHS Overview for CWS Staff-** 1 hr

* eLearning
* To include CYF BHS Assessment tool overview, Org Chart
* To include focus on moving forward with Pathways to Well Being
* Target completion: Nov-2013

*Curriculum Lead: BHETA; Contract: BHETA*

**Class & Subclass Identification Training**

* Review of criteria for meeting class and subclass definition
* Review of how and when to use the ICC and IHBS codes
* Audience: BHS staff and providers
* Roll out: October- 2013

*Curriculum Lead: QI*

**Transition –** 3 hr module

* Includes: Strategies for identifying key times of transition; Strategies for preparing youth & family for transitions; Continued engagement with CFT; Aftercare planning
* Audience: CWS staff, BHS staff and providers
* Design completion:
* Roll out: May-June, 2014

*Curriculum Lead: BHETA; Contract: BHETA*

**Monitoring and Adapting –** 3 hr module

* Includes: Strategies for monitoring needs & plan; Maintaining family/youth voice; Continued engagement/communication with CFT; Flexibility and adaptations to the plan
* Audience: CWS staff, BHS staff and providers
* Design completion: Mar, 2014
* Roll out: April-May, 2014

*Curriculum Lead: BHETA; Contract: BHETA*

**Teaming Training –** 3 hr module

* Includes: How to create a CFT; How to facilitate communication between CFT members; Facilitation skills training/CFT meeting skill practice; Engagement with CFT
* Audience: CWS staff, BHS staff and providers
* Design completion: Feb, 2014
* Roll out: Mar-Apr, 2014

*Curriculum Lead: PCWTA; Contract: PCWTA*